## Cover
MyriadSea
Vessel Inspection Report
<SHIP>
<DATE>
<PLACE>
<INSPECTOR>
<INSPECTOR>

## i. Preface
i. Preface
The purpose of this report is to give an indication of the condition of the vessel (or of a specific part of the vessel, as indicated) at a specific moment in time and to indicate in what way the condition has changed since the last inspection was carried out. It is intended to indicate where improvements can, should and must be made.
In rating each item/ area inspected, the inspector should take account of objective evidence physically observed, of recent reports and communications and of comments or observations made by ship’s staff.
The following system of assessment will be used:
| SATISFACTORY | The item is in a good condition, is being maintained well and no action is required. | 1
| FAIR | The item is in an acceptable condition, and is being maintained to an acceptable standard. While there is room for improvement, there is no specific issue to address. | 2
| MINOR ISSUE | Minor issue(s): Improvements required. Below standard. Attention and action is required. | 3
| MAJOR ISSUE | Major issue(s): Corrective action required as soon as possible. Major operation defect that could cause problems with external inspectors. | 4
| NOT SEEN | Not seen due to lack of access, lack of required permission or lack of time during this inspection | NS
| NOT APPLICABLE | Not applicable to this vessel | NA
Where a given rating is based on observations from ship staff a comment to that effect should be entered against that item.
Where issues are identified during internal inspections, corrective action to be should, wherever practical, be identifiable from the comments made in this report. Defects identified should be entered into a section H defect report. When all defects have been closed out, the completed section H should be attached to this report.
A copy of this report should be sent to the vessel as soon as practical after the inspection has taken place, where it should be retained in the ship’s records.

## ii. Inspection Details
ii. Inspection Details
Date(s)
Port
Inspector(s)
Officers
Master
Chief Engineer
Chief Officer
Second Engineer
Electrician
Purpose of the inspection & specific exclusions (if any)
Sections included in this report:
A | Bridge/ Deck/ Cargo
B | Tanks, Bunkering, Bilge Systems
C | Safety Equipment
D | Machinery Spaces & Auxiliary Equipment
E | Accommodation
F | Certification/ Legislation/ Environment
G | Photo Report
H | Defect Report
I | Personnel: Crew List
J | Personnel: Inspectors Assessment
Inspector(s):

## A. Deck Bridge Cargo
A. HULL/ DECK/ CARGO | [11 empty] | 2020-07-07
[5 empty] | THIS SECTION IS NOT PRINTED | [6 empty] | 2020-07-07
Hull & Decks | [11 empty] | 2020-07-07
2020-07-07
A1 Hull - Plating/ Coating | [11 empty] | 2020-07-07
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) | Rating | ID | Observations & Corrective Action Required | Closeout Date | 2020-07-07
1.1 | Top Sides | Top Sides |  | 2 | [7 empty] | 2020-07-07
1.2 | Vertical Sides | Vertical Sides |  | 1 | [7 empty] | 2020-07-07
1.3 | Flat Bottom | Flat Bottom |  | NS | [7 empty] | 2020-07-07
1.4 | Rudder | Rudder |  | 2 | [7 empty] | 2020-07-07
1.5 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A2 Decks | [11 empty] | 2020-07-07
2.1 | Forecastle | Forecastle |  | 2 | [7 empty] | 2020-07-07
2.2 | Stern | Stern |  | 1 | [7 empty] | 2020-07-07
2.3 | Cargo Deck | Cargo Deck |  | 2 | [7 empty] | 2020-07-07
2.4 | Accommodation External | Accommodation External | Various External ladders in need of repair. All to be inspected and those in poor condition to be repaired. | 3 |  | y | 90 | 3 | 2.4 | Various External ladders in need of repair. All to be inspected and those in poor condition to be repaired. | 2020-10-05 | 2020-07-07
2.5 | Bridge Wings | Bridge Wings |  | 1 | [7 empty] | 2020-07-07
2.6 | Compass Deck | Compass Deck |  | 2 | [7 empty] | 2020-07-07
2.7 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A3 Shipside Rails/ Bulwarks | [11 empty] | 2020-07-07
3.1 | Side Rails |  |  | 2 | [7 empty] | 2020-07-07
3.2 | Bulwarks |  | Midships Stbd Side: Various cracks, likely result of cargo damage. Chief Officer to inspect and arrange necessary repairs | 3 |  | y | 90 | 3 | 3.2 | Midships Stbd Side: Various cracks, likely result of cargo damage. Chief Officer to inspect and arrange necessary repairs | 2020-10-05 | 2020-07-07
3.3 | Other |  |  | NA | [7 empty] | 2020-07-07
2020-07-07
Mooring Equipment, Windlass, Anchors, Chain Lockers | [11 empty] | 2020-07-07
2020-07-07
A4 Forward Mooring Winches | [11 empty] | 2020-07-07
4.1 | Cosmetic Condition | Cosmetic Condition |  | 2 | [7 empty] | 2020-07-07
4.2 | Operational Condition | Operational Condition |  | 1 | [7 empty] | 2020-07-07
4.3 | Brake Lining / Linkages | Brake Lining / Linkages |  | 1 | [7 empty] | 2020-07-07
4.4 | Safety / Rails / Guards / Signs | Safety / Rails / Guards / Signs |  | 2 | [7 empty] | 2020-07-07
4.5 | Elect / Hyd Condition | Elect / Hyd Condition |  | NS | [7 empty] | 2020-07-07
4.6 | Rope Condition | Rope Condition | Rope renewal programme ongoing | 1 | [7 empty] | 2020-07-07
4.7 | Other | Other | Mooring winch operator platforms: Wooden board that makes up middle platform is missing, causing the rest to move away from their seating. Middle board to be replaced immediately, and the condition of all remaining boards to be inspected and repairs or adjustments made to ensure they cannot "slide" free. | 4 |  | y | 5 | 4 | 4.7 | Mooring winch operator platforms: Wooden board that makes up middle platform is missing, causing the rest to move away from their seating. Middle board to be replaced immediately, and the condition of all remaining boards to be inspected and repairs or adjustments made to ensure they cannot "slide" free. | 2020-07-12 | 2020-07-07
2020-07-07
A5 Anchors/ Windlass(es) | [11 empty] | 2020-07-07
5.1 | Cosmetic Condition | Cosmetic Condition |  | 2 | [7 empty] | 2020-07-07
5.2 | Operational Condition | Operational Condition |  | NS | [7 empty] | 2020-07-07
5.3 | Brake Lining / Linkages | Brake Lining / Linkages |  | 1 | [7 empty] | 2020-07-07
5.4 | Safety / Rails / Guards / Signs | Safety / Rails / Guards / Signs |  | 2 | [7 empty] | 2020-07-07
5.5 | Hyd Condition | Hyd Condition |  | NS | [7 empty] | 2020-07-07
5.6 | Anchor / Chain Condition | Anchor / Chain Condition |  | NS | [7 empty] | 2020-07-07
5.7 | Spare Anchor | Spare Anchor |  | NS | [7 empty] | 2020-07-07
5.8 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A6Chain Lockers/ Hawsers/ Spurling Pipes | [11 empty] | 2020-07-07
6.1 | Coatings | Coatings |  | 2 | [7 empty] | 2020-07-07
6.2 | Mechanical Damage | Mechanical Damage |  | 1 | [7 empty] | 2020-07-07
6.3 | Bitter End Attachment | Bitter End Attachment |  | NS | [7 empty] | 2020-07-07
6.4 | Bell Mouth / Spurling Pipe | Bell Mouth / Spurling Pipe |  | 1 | [7 empty] | 2020-07-07
6.5 | Bilge Pumping Arrangements | Bilge Pumping Arrangements |  | NS | [7 empty] | 2020-07-07
6.6 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A7 Aft Mooring Winches | [11 empty] | 2020-07-07
7.1 | Cosmetic Condition | Cosmetic Condition |  | 1 | [7 empty] | 2020-07-07
7.2 | Operational Condition | Operational Condition |  | NS | [7 empty] | 2020-07-07
7.3 | Brake Lining / Linkages | Brake Lining / Linkages |  | 1 | [7 empty] | 2020-07-07
7.4 | Safety / Rails / Guards / Signs | Safety / Rails / Guards / Signs |  | 1 | [7 empty] | 2020-07-07
7.5 | Hyd / E−motor Condition | Hyd / E−motor Condition |  | 1 | [7 empty] | 2020-07-07
7.6 | Rope Condition | Rope Condition |  | 1 | [7 empty] | 2020-07-07
7.7 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A8 Mooring Bits / Rollers / Fairleads / Bollards / Capstans | [11 empty] | 2020-07-07
8.1 | Cosmetic Condition | Cosmetic Condition |  | 2 |  | n | [5 empty] | 2020-07-07
8.2 | Operational Condition | Operational Condition |  | NS | [7 empty] | 2020-07-07
8.3 | Mooring Practice | Mooring Practice |  | 1 | [7 empty] | 2020-07-07
8.4 | Safety | Safety | Refer A4.7 | 3 |  | n | [5 empty] | 2020-07-07
8.5 | Emerg Towing Rope | Emerg Towing Rope |  | NS | [7 empty] | 2020-07-07
8.6 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A9 Deck Equipment | [11 empty] | 2020-07-07
9.1 | Accom Gangways / Winches | Accom Gangways / Winches |  | 1 | [7 empty] | 2020-07-07
9.2 | Date Wires Renewed (max 30month): | Date Wires Renewed (max 30month): |  | 1 | [7 empty] | 2020-07-07
9.3 | Date Last Load Test | Date Last Load Test |  | 1 | [7 empty] | 2020-07-07
9.4 | Condition Check of Limit Switch | Condition Check of Limit Switch |  | NS | [7 empty] | 2020-07-07
9.5 | Pilot Embarkation Areas | Pilot Embarkation Areas |  | 1 | [7 empty] | 2020-07-07
9.6 | Pilot Ladder Reels / Winch | Pilot Ladder Reels / Winch |  | 1 | [7 empty] | 2020-07-07
9.7 | Stores Crane | Stores Crane |  | 1 | [7 empty] | 2020-07-07
9.8 | Date Wires Renewed (max 30month): | Date Wires Renewed (max 30month): |  | 1 | [7 empty] | 2020-07-07
9.9 | Date Last Load Test | Date Last Load Test |  | 1 | [7 empty] | 2020-07-07
9.1 | Condition Check of Limit Switch | Condition Check of Limit Switch |  | NS | [7 empty] | 2020-07-07
2020-07-07
A10 Deck Electrical | [11 empty] | 2020-07-07
10.1 | Conduits / Trays | Conduits / Trays |  | 1 | [7 empty] | 2020-07-07
10.2 | Light Fittings / Junction Boxes | Light Fittings / Junction Boxes |  | 1 | [7 empty] | 2020-07-07
10.3 | Panama / Gangway Lights | Panama / Gangway Lights | Not function tested, visible condition only | 1 | [7 empty] | 2020-07-07
10.4 | Emerg Lighting | Emerg Lighting |  | NS | [7 empty] | 2020-07-07
10.5 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A11 Deck Piping | [11 empty] | 2020-07-07
11.1 | Compressed Air | Compressed Air |  | 1 | [7 empty] | 2020-07-07
11.2 | Fresh Water | Fresh Water |  | 1 | [7 empty] | 2020-07-07
11.3 | Fire Line | Fire Line |  | 1 | [7 empty] | 2020-07-07
11.4 | Identification | Identification |  | 1 | [7 empty] | 2020-07-07
11.5 | Other | Other |  | 1 | [7 empty] | 2020-07-07
2020-07-07
Access Hatches, Booby Hatches, Watertight / Weather tight doors, Ventilation | [11 empty] | 2020-07-07
2020-07-07
A12 Access Hatches | [11 empty] | 2020-07-07
12.1 | Forecastle | Forecastle |  | 2 | [7 empty] | 2020-07-07
12.2 | Cargo Deck | Cargo Deck |  | 2 | [7 empty] | 2020-07-07
12.3 | Poop Deck | Poop Deck |  | NA | [7 empty] | 2020-07-07
12.4 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A13 Watertight / Weathertight Doors | [11 empty] | 2020-07-07
13.1 | Forecastle | Forecastle |  | 2 | [7 empty] | 2020-07-07
13.2 | Accommodation / Funnel | Accommodation / Funnel | Various handles and hinges corroded. Monitor. | 3 | [7 empty] | 2020-07-07
13.3 | Poop Deck | Poop Deck |  | 1 | [7 empty] | 2020-07-07
13.4 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A14 Ventilation - Natural / Forced | [11 empty] | 2020-07-07
14.1 | Forecastle | Forecastle |  | 2 | [7 empty] | 2020-07-07
14.2 | Fire Flaps / Dampers | Fire Flaps / Dampers |  | 2 | [7 empty] | 2020-07-07
14.3 | Verification Test | Verification Test by TSI |  | NA | [7 empty] | 2020-07-07
14.4 | Cargo Holds | Cargo Holds | Not seen due to ongoing cargo operations | NS | [7 empty] | 2020-07-07
14.5 | Fire Flaps / Dampers | Fire Flaps / Dampers |  | 2 | [7 empty] | 2020-07-07
14.6 | Verification Test | Verification Test by TSI |  | NA | [7 empty] | 2020-07-07
14.7 | Deck Houses | Deck Houses | Some fire flaps found to be corroded. Rectification plan to be drawn up and submitted to Technical Department. | 3 |  | y | 60 | 3 | 14.7 | Some fire flaps found to be corroded. Rectification plan to be drawn up and submitted to Technical Department. | 2020-09-05 | 2020-07-07
14.8 | Fire Flaps / Dampers | Fire Flaps / Dampers |  | NS | [7 empty] | 2020-07-07
14.9 | Verification Test | Verification Test by TSI |  | NA | [7 empty] | 2020-07-07
14.1 | Poop Deck | Poop Deck |  | 2 | [7 empty] | 2020-07-07
14.11 | Fire Flaps / Dampers | Fire Flaps / Dampers | Some fire flaps found to be corroded. Rectification plan to be drawn up and submitted to Technical Department. | 3 |  | y | 60 | 3 | 14.11 | Some fire flaps found to be corroded. Rectification plan to be drawn up and submitted to Technical Department. | 2020-09-05 | 2020-07-07
14.12 | Verification Test | Verification Test by TSI |  | NA | [7 empty] | 2020-07-07
14.13 | Engine Room | Engine Room |  | 2 | [7 empty] | 2020-07-07
14.14 | Fire Flaps / Dampers | Fire Flaps / Dampers |  | 2 | [7 empty] | 2020-07-07
14.15 | Verification Test | Verification Test by TSI |  | NA | [7 empty] | 2020-07-07
14.16 | Paint Locker | Paint Locker |  | 2 | [7 empty] | 2020-07-07
14.17 | CO2 Room | CO2 Room |  | 2 | [7 empty] | 2020-07-07
14.18 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A15 Anti Piracy / ISPS | [11 empty] | 2020-07-07
15.1 | Accommodation Access | Accommodation Access | At time of arrival there was no gangway watchman present, he had been removed to carry out other tasks by the Chief Officer. The Visitor Record is not being consistently completed. All crew are to be reminded of the requirements of ISPS with respect to Access Control and Safety. Gangway watch crew are to be reminded to NEVER leave the access point. | 4 |  | y | 10 | 4 | 15.1 | At time of arrival there was no gangway watchman present, he had been removed to carry out other tasks by the Chief Officer. The Visitor Record is not being consistently completed. All crew are to be reminded of the requirements of ISPS with respect to Access Control and Safety. Gangway watch crew are to be reminded to NEVER leave the access point. | 2020-07-17 | 2020-07-07
15.2 | ERM Access | ERM Access |  | NA | [7 empty] | 2020-07-07
15.3 | Cargo Hold Access | Cargo Hold Access |  | NA | [7 empty] | 2020-07-07
15.4 | Focsle / Stern | Focsle / Stern |  | NA | [7 empty] | 2020-07-07
15.5 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
Cargo Holds, Hatch Covers, Coamings, Hydraulics | [11 empty] | 2020-07-07
2020-07-07
A16 Cargo Holds | [11 empty] | 2020-07-07
| Cargo Hold 1 | Cargo Hold 1 | [9 empty] | 2020-07-07
16.1.1 | Coatings | Coatings |  | 2 | [7 empty] | 2020-07-07
16.1.2 | Steel Structure | Steel Structure |  | 2 | [7 empty] | 2020-07-07
16.1.3 | Ladders / Platforms | Ladders / Platforms |  | 2 | [7 empty] | 2020-07-07
16.1.4 | Piping / Guards | Piping / Guards |  | 2 | [7 empty] | 2020-07-07
16.1.5 | Fire Flaps / DamperS | Fire Flaps / DamperS |  | 2 | [7 empty] | 2020-07-07
16.1.6 | Hatch covers | CH 1 Hatch covers | At completion of cargo operations, CH1 hatch cover was severely damaged, resulting in delay of approx 2 days. | 4 |  | y | 0 | 4 | 16.1.6 | At completion of cargo operations, CH1 hatch cover was severely damaged, resulting in delay of approx 2 days. | 2020-07-07 | 2020-07-07
16.1.7 | Coatings | Coatings | Fair only | 3 | [7 empty] | 2020-07-07
16.1.8 | Steel Structure | Steel Structure |  | 1 | [7 empty] | 2020-07-07
16.1.9 | Fittings | Fittings |  | 1 | [7 empty] | 2020-07-07
16.1.10 | Rubber Packing | Rubber Packing |  | 1 | [7 empty] | 2020-07-07
16.1.11 | Coamings | Coamings |  | 2 | [7 empty] | 2020-07-07
16.1.12 | Other | Other | Many hatch cover cleats either missing or damaged. Understood repair plan in place, to be monitored closely. | 4 |  | y | 120 | 4 | 16.1.12 | Many hatch cover cleats either missing or damaged. Understood repair plan in place, to be monitored closely. | 2020-11-04 | 2020-07-07
2020-07-07
| Cargo Hold 2 | Cargo Hold 1 | [9 empty] | 2020-07-07
16.2.1 | Coatings | Coatings |  | 2 | [7 empty] | 2020-07-07
16.2.2 | Steel Structure | Steel Structure |  | 2 | [7 empty] | 2020-07-07
16.2.3 | Ladders / Platforms | Ladders / Platforms |  | 1 | [7 empty] | 2020-07-07
16.2.4 | Piping / Guards | Piping / Guards |  | 1 | [7 empty] | 2020-07-07
16.2.5 | Fire Flaps / DamperS | Fire Flaps / DamperS |  | 1 | [7 empty] | 2020-07-07
16.2.6 | Hatch covers | CH 1 Hatch covers |  | 1 | [7 empty] | 2020-07-07
16.2.7 | Fittings | Fittings |  | 1 | [7 empty] | 2020-07-07
16.2.8 | Rubber Packing | Rubber Packing |  | 1 | [7 empty] | 2020-07-07
16.2.9 | Coamings | Coamings |  | 1 | [7 empty] | 2020-07-07
16.2.10 | Other | Other | Refer A16.1.12 | 4 |  | n | [5 empty] | 2020-07-07
2020-07-07
A17 Cargo Cranes | [11 empty] | 2020-07-07
17.1 | Crane 1 | Crane 1 |  | 1 | [7 empty] | 2020-07-07
17.2 | Wires condition / Renewed | Wires condition / Renewed |  | 1 | [7 empty] | 2020-07-07
17.3 | Oil Analysis | Oil Analysis |  | NS | [7 empty] | 2020-07-07
17.4 | Machinery Space | Machinery Space | Not seen due to ongoing cargo operations | NS | [7 empty] | 2020-07-07
17.5 | Wire Ropes / Sheave / Blocks | Wire Ropes / Sheave / Blocks | Not seen due to ongoing cargo operations | NS | [7 empty] | 2020-07-07
17.6 | Safety / Signage | Safety / Signage |  | 1 | [7 empty] | 2020-07-07
17.7 | Crane Cabin | Crane Cabin | Not seen due to ongoing cargo operations | NS | [7 empty] | 2020-07-07
17.8 | Other | Other |  | NA | [7 empty] | 2020-07-07
17.9 | Crane 2 | Crane 2 |  | 1 | [7 empty] | 2020-07-07
17.1 | Wires condition / Renewed | Wires condition / Renewed |  | 1 | [7 empty] | 2020-07-07
17.11 | Oil Analysis | Oil Analysis |  | 1 | [7 empty] | 2020-07-07
17.12 | Machinery Space | Machinery Space | Not seen due to ongoing cargo operations | NS | [7 empty] | 2020-07-07
17.13 | Wire Ropes / Sheave / Blocks | Wire Ropes / Sheave / Blocks |  | NS | [7 empty] | 2020-07-07
17.14 | Safety / Signage | Safety / Signage |  | 1 | [7 empty] | 2020-07-07
17.15 | Crane Cabin | Crane Cabin | Not seen due to ongoing cargo operations | NS | [7 empty] | 2020-07-07
17.16 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A18 Cargo Securing Gear / Timber Stanchions | [11 empty] | 2020-07-07
18.1 | Fixed Stanchions | Fixed Stanchions |  | NS | [7 empty] | 2020-07-07
18.2 | Wires/ Chains/ Shackles/ Grips/ etc | Wires/ Chains/ Shackles/ Grips/ etc | Not seen due to ongoing cargo operations | NS | [7 empty] | 2020-07-07
18.3 | Container Lashing material | Container Lashing material | Not seen due to ongoing cargo operations | NS | [7 empty] | 2020-07-07
18.4 | Date Last Inventory: | Date Last Inventory: |  | NS | [7 empty] | 2020-07-07
18.5 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
Deck Structures – External/ Internal | [11 empty] | 2020-07-07
2020-07-07
A19 Deck Structures – External | [11 empty] | 2020-07-07
19.1 | Fwd Mast/ Equipment | Fwd Mast/ Equipment | Ladder access showing signs of corrosions. To be monitored. | 3 |  | n | [5 empty] | 2020-07-07
19.2 | Deck Houses | Deck Houses | Midships deck house, fire flap on top of structure, corroded. To be repaired. | 3 |  | n | [5 empty] | 2020-07-07
19.3 | Radar Mast/ Xmas Tree | Radar Mast/ Xmas Tree | Ladder to radar mast beginning to corrode. To be chipped and re-coated at earliest opportunity. | 3 |  | n | [5 empty] | 2020-07-07
19.4 | Accommodation Block | Accommodation Block | External ladders require coating to prevent the spread of corrosion. | 3 |  | n | [5 empty] | 2020-07-07
19.5 | ERM Casing | ERM Casing | Corrosion. | 3 |  | n | [5 empty] | 2020-07-07
19.6 | Funnel/ Top Hat | Funnel/ Top Hat | Lifting lugs corroded. Repair plan to be submitted and lugs not to be used until repaired. | 3 |  | n | [5 empty] | 2020-07-07
19.7 | Other | Other | Significant corrosion around deck structures, including fire flaps, doors ladders and lifting lugs. Chief Officer to carry out a full inspection of the deck area and to prepare and submit a repair plan to the Technical Department. | 4 |  | y | 30 | 4 | 19.7 | Significant corrosion around deck structures, including fire flaps, doors ladders and lifting lugs. Chief Officer to carry out a full inspection of the deck area and to prepare and submit a repair plan to the Technical Department. | 2020-08-06 | 2020-07-07
2020-07-07
A20 Deck Structures – Internal | [11 empty] | 2020-07-07
20.1 | Focsle Space | Focsle Space | Housekeeping standards to be improved. | 3 |  | n | [5 empty] | 2020-07-07
20.2 | WIDS − date last tested: | WIDS − date last tested: |  | NS | [7 empty] | 2020-07-07
20.3 | Deck Houses | Deck Houses |  | 1 | [7 empty] | 2020-07-07
20.4 | Paint Locker | Paint Locker | General housekeeping to be improved. Paint to be properly stowed, and crew to be reminded of the importance of doing so. | 3 |  | y | 30 | 3 | 20.4 | General housekeeping to be improved. Paint to be properly stowed, and crew to be reminded of the importance of doing so. | 2020-08-06 | 2020-07-07
20.5 | Store Rooms | Store Rooms | General housekeeping to be improved. | 3 |  | n | [5 empty] | 2020-07-07
20.6 | SOPEP Locker | SOPEP Locker | Not seen as repairs underway in space during inspection | NS | [7 empty] | 2020-07-07
20.7 | Deck Workshop | Deck Workshop | General housekeeping to be improved. | 3 |  | n | [5 empty] | 2020-07-07
20.8 | Funnel | Funnel |  | 1 | [7 empty] | 2020-07-07
20.9 | Welding Locker | Oxy Acet Locker | Half-full drum of waste oil and dirty rags being stored in this space. To be removed immediately and crew to be reminded that this is not acceptable at any time. | 4 |  | y | 10 | 4 | 20.9 | Half-full drum of waste oil and dirty rags being stored in this space. To be removed immediately and crew to be reminded that this is not acceptable at any time. | 2020-07-17 | 2020-07-07
20.1 | Steering Space | Steering Space | Very good condition. | 1 | [7 empty] | 2020-07-07
20.11 | Aft Rope Store | Aft Rope Store |  | NA | [7 empty] | 2020-07-07
20.12 | Emergency Escape | Emergency Escape | Almost all of the ships vertical escapes have no safety chain at their upper end. To be ordered and installed. Escape from ER Lower Deck Fwd Stbd, plating corroded through. To be investigated. | 4 |  | y | 30 | 4 | 20.12 | Almost all of the ships vertical escapes have no safety chain at their upper end. To be ordered and installed. Escape from ER Lower Deck Fwd Stbd, plating corroded through. To be investigated. | 2020-08-06 | 2020-07-07
20.13 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
Bridge Area / Equipment | [11 empty] | 2020-07-07
2020-07-07
A21 Bridge Area | [11 empty] | 2020-07-07
21.1 | Cosmetic Condition | Cosmetic Condition |  | 1 | [7 empty] | 2020-07-07
21.2 | Stowage/ Storage | Stowage/ Storage |  | 1 | [7 empty] | 2020-07-07
21.3 | Ablution | Ablution |  | 2 | [7 empty] | 2020-07-07
21.4 | Lighting/ Ventilation | Lighting/ Ventilation |  | 1 | [7 empty] | 2020-07-07
21.5 | Electrical | Electrical |  | 1 | [7 empty] | 2020-07-07
21.6 | Bridge Wings | Bridge Wings |  | 1 | [7 empty] | 2020-07-07
21.7 | Other | Other | Clean, tidy andwell maintained. | 1 | [7 empty] | 2020-07-07
2020-07-07
A22 Navigation Equipment | [11 empty] | 2020-07-07
22.1 | Magnetic Compass | Magnetic Compass |  | 1 | [7 empty] | 2020-07-07
22.2 | Date last adjusted / swung: | Date last adjusted / swung: |  | NS | [7 empty] | 2020-07-07
22.3 | Gyro Compass | Gyro Compass | Newly re-fitted after repairs ashore. | 1 | [7 empty] | 2020-07-07
22.4 | Date Service (Time 15−18month): | Date Service (Time 15−18month): | 2015-12-01 | 1 | [7 empty] | 2020-07-07
22.5 | Sphere Renewed / Dev: | Sphere Renewed / Dev: | 2015-12-01 | 1 | [7 empty] | 2020-07-07
22.6 | Radar − X Band | Radar − X Band | No reported issues | 1 | [7 empty] | 2020-07-07
22.7 | Date last service / Mag renewed: | Date last service / Mag renewed: |  | NS | [7 empty] | 2020-07-07
22.8 | Radar − S Band | Radar − S Band | No reported issues | 1 | [7 empty] | 2020-07-07
22.9 | Date last service / Mag renewed: | Date last service / Mag renewed: |  | NS | [7 empty] | 2020-07-07
22.1 | AIS | AIS | No reported issues | 1 | [7 empty] | 2020-07-07
22.11 | GPS 1 | GPS 1 |  | 1 | [7 empty] | 2020-07-07
22.12 | GPS 2 | GPS 2 |  | 1 | [7 empty] | 2020-07-07
22.13 | Speed Log | Speed Log |  | 1 | [7 empty] | 2020-07-07
22.14 | Echo Sounder | Echo Sounder |  | 1 | [7 empty] | 2020-07-07
22.15 | Navigation Lights | Navigation Lights |  | 1 | [7 empty] | 2020-07-07
22.16 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A23 Communication Equipment | [11 empty] | 2020-07-07
23.1 | Sat C | Sat C |  | 1 | [7 empty] | 2020-07-07
23.2 | SSAS | SSAS |  | 1 | [7 empty] | 2020-07-07
23.3 | GMDSS Station | GMDSS Station |  | 1 | [7 empty] | 2020-07-07
23.4 | GMDSS VHF 3x Handhelds | GMDSS VHF 3x Handhelds |  | 1 | [7 empty] | 2020-07-07
23.5 | Date Li Batts Expire: | Date Li Batts Expire: |  | NS | [7 empty] | 2020-07-07
23.6 | VHF Sets x 2 | VHF Sets x 2 |  | 1 | [7 empty] | 2020-07-07
23.7 | DSC | DSC |  | 1 | [7 empty] | 2020-07-07
23.8 | MF / HF | MF / HF |  | 1 | [7 empty] | 2020-07-07
23.9 | Weather Fax | Weather Fax |  | 1 | [7 empty] | 2020-07-07
23.1 | Navtex | Navtex |  | 1 | [7 empty] | 2020-07-07
23.11 | Epirb | Epirb |  | 1 | [7 empty] | 2020-07-07
23.12 | Date Batt / HRU Expire: | Date Batt / HRU Expire: |  | 1 | [7 empty] | 2020-07-07
23.13 | SART's | SART's |  | 1 | [7 empty] | 2020-07-07
23.14 | Date Batt Expire: | Date Batt Expire: |  | 1 | [7 empty] | 2020-07-07
23.15 | VDR | VDR |  | 1 | [7 empty] | 2020-07-07
23.16 | Date Last Annual Service: | Date Last Annual Service: |  | 1 | [7 empty] | 2020-07-07
23.17 | Portable VHF / UHF's | Portable VHF / UHF's |  | NS | [7 empty] | 2020-07-07
23.18 | No. Onboard | No. Onboard |  | NS | [7 empty] | 2020-07-07
23.19 | Computers | Computers | No reported issues, all communications being received | 1 | [7 empty] | 2020-07-07
23.2 | No. Onboard | No. Onboard |  | NA | [7 empty] | 2020-07-07
23.21 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A24 Publications / Charts / NTM's | [11 empty] | 2020-07-07
24.1 | Charts | Charts |  | 1 | [7 empty] | 2020-07-07
24.2 | Number of folios in use / sleeping: | Number of folios in use / sleeping: |  | 1 | [7 empty] | 2020-07-07
24.3 | Publications | Publications |  | 1 | [7 empty] | 2020-07-07
24.4 | NTM's | NTM's |  | 1 | [7 empty] | 2020-07-07
24.5 | Latest NTM corrected / date | Latest NTM corrected / date |  | 1 | [7 empty] | 2020-07-07
24.6 | Latest NTM onbd / Date recvd: | Latest NTM onbd / Date recvd: |  | 1 | [7 empty] | 2020-07-07
24.7 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
A25 Bridge Records, Logs and Orders | [11 empty] | 2020-07-07
25.1 | Bridge Log Book |  | Completed | 1 | [7 empty] | 2020-07-07
25.2 | Compass Error Book |  | Completed regularly | 1 | [7 empty] | 2020-07-07
25.3 | Other records |  |  | 1 | [7 empty] | 2020-07-07
25.4 | Masters Night Orders |  | Masters night orders only completed sporadically. To be completed every night the vessel is at sea. | 4 |  | y | 1 | 4 | 25.4 | Masters night orders only completed sporadically. To be completed every night the vessel is at sea. | 2020-07-08 | 2020-07-07
25.5 | Other |  |  | NA | [7 empty] | 2020-07-07
2020-07-07
2020-07-07
2020-07-07

## B. Tanks Bunkering Bilge System
B. TANKS, BUNKERING, BILGE SYSTEMS
THIS SECTION IS NOT PRINTED
B1 Ballast Tanks
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) | Rating | ID | Observations & Corrective Action Required | Closeout Date | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
B2 Void Spaces | [11 empty] | 2020-07-07
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) |  |  |  |  | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
B3 FW Tanks | [11 empty] | 2020-07-07
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) |  |  |  |  | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
B4 Cargo Tanks (Where applicable) | [11 empty] | 2020-07-07
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) |  |  |  |  | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
B5 HFO / MDO Bunker Tanks | [11 empty] | 2020-07-07
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) |  |  |  |  | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
B6 Free Standing LO / Sludge / FO Tanks | [11 empty] | 2020-07-07
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) |  |  |  |  | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
B7 Bunkering System | [11 empty] | 2020-07-07
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) |  |  |  |  | 2020-07-07
7.1 | Fuel Manifold | Fuel Manifold | [9 empty] | 2020-07-07
7.2 | Date Last Pressure Tested: | Date Last Pressure Tested: | [9 empty] | 2020-07-07
7.3 | Sampling | Sampling | [9 empty] | 2020-07-07
7.4 | LO Manifold | LO Manifold | [9 empty] | 2020-07-07
7.5 | Sludge / Sewage Manifold | Sludge / Sewage Manifold | [9 empty] | 2020-07-07
7.6 | FW Manifold | FW Manifold | [9 empty] | 2020-07-07
7.7 | Savealls | Savealls | [9 empty] | 2020-07-07
7.8 | Other | Other | [9 empty] | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07

## C. Safety Equipment
C. SAFETY EQUIPMENT
THIS SECTION IS NOT PRINTED
Life-Saving Appliances
C1 Lifeboats & Davits
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) | Rating | ID | Observations & Corrective Action Required | Closeout Date | 2020-07-07
1.1 | Free Fall Boat / Engine / Equipment |  |  | 1 | [7 empty] | 2020-07-07
1.2 | Date Wires Renewed (max 30month): | Date Wires Renewed (max 30month): |  | 1 | [7 empty] | 2020-07-07
1.3 | Date Last Load Test | Date Last Load Test |  | 1 | [7 empty] | 2020-07-07
1.4 | Condition Check of Limit Switch | Condition Check of Limit Switch |  | 1 | [7 empty] | 2020-07-07
1.5 | Rescue Boat / Engine / Equipment | Rescue Boat / Engine / Equipment | Condition of recure boat coating deteriorating. In places fibreglass is visible. To be monintored, and touched up when practical. | 2 | [7 empty] | 2020-07-07
1.6 | Date last launched: | Date last launched: |  | 1 | [7 empty] | 2020-07-07
1.7 | Rescue Boat Crane | Rescue Boat Crane |  | 1 | [7 empty] | 2020-07-07
1.8 | Date Wires Renewed (max 30month): | Date Wires Renewed (max 30month): |  | 1 | [7 empty] | 2020-07-07
1.9 | Date Last Load Test | Date Last Load Test |  | 1 | [7 empty] | 2020-07-07
1.1 | Condition Check of Limit Switch | Condition Check of Limit Switch |  | 1 | [7 empty] | 2020-07-07
1.11 | Launch area and surrounds | Launch area and surrounds |  | 1 | [7 empty] | 2020-07-07
1.12 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
C2 Liferafts | [11 empty] | 2020-07-07
2.1 | Free Fall Boat / Engine / Equipment |  |  | 1 | [7 empty] | 2020-07-07
2.2 | Date Wires Renewed (max 30month): | Date Wires Renewed (max 30month): |  | 1 | [7 empty] | 2020-07-07
2.3 | Date Last Load Test | Date Last Load Test |  | 1 | [7 empty] | 2020-07-07
2.4 | Condition Check of Limit Switch | Condition Check of Limit Switch |  | 1 | [7 empty] | 2020-07-07
2.5 | Rescue Boat / Engine / Equipment | Rescue Boat / Engine / Equipment |  | 1 | [7 empty] | 2020-07-07
2.6 | Date last launched: | Date last launched: |  | 1 | [7 empty] | 2020-07-07
2.7 | Rescue Boat Crane | Rescue Boat Crane |  | 1 | [7 empty] | 2020-07-07
2.8 | Date Wires Renewed (max 30month): | Date Wires Renewed (max 30month): |  | 1 | [7 empty] | 2020-07-07
2.9 | Date Last Load Test | Date Last Load Test |  | 1 | [7 empty] | 2020-07-07
2.1 | Condition Check of Limit Switch | Condition Check of Limit Switch |  | 1 | [7 empty] | 2020-07-07
2.11 | Launch area and surrounds | Launch area and surrounds |  | 1 | [7 empty] | 2020-07-07
2.12 | Other | Other | All liferafts serviced and correctly stowed. | NA | [7 empty] | 2020-07-07
2020-07-07
C3 Other Safety Equipment | [11 empty] | 2020-07-07
2.1 | MOB Smoke Floats | MOB Smoke Floats |  | 1 | [7 empty] | 2020-07-07
2.2 | Date Smoke Floats Expire: | Date Smoke Floats Expire: | 2016 | [8 empty] | 2020-07-07
2.3 | Lifejackets | Lifejackets |  | 1 | [7 empty] | 2020-07-07
2.4 | Nr Onbd / Lights Expire: | Nr Onbd / Lights Expire: | [9 empty] | 2020-07-07
2.5 | Life rings | Life rings |  | 2 | [7 empty] | 2020-07-07
2.6 | Immersion Suits | Immersion Suits | [9 empty] | 2020-07-07
2.7 | Nr Onbd / Lights Expire: | Nr Onbd / Lights Expire: | [9 empty] | 2020-07-07
2.8 | Immersion suit pressure test date being monitored | Immersion suit pressure test date being monitored | [9 empty] | 2020-07-07
2.9 | Pyrotechnics | Pyrotechnics | [9 empty] | 2020-07-07
2.1 | Date Expire: | Date Expire: | [9 empty] | 2020-07-07
2.11 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
Fire-Fighting Equipment | [11 empty] | 2020-07-07
2020-07-07
C4 Fixed Fire Fighting Systems | [11 empty] | 2020-07-07
4.1 | ERM / HOLD CO2 | ERM / HOLD CO2 |  | NS | [7 empty] | 2020-07-07
4.2 | Date Last Serviced: | Date Last Serviced: |  | NS | [7 empty] | 2020-07-07
4.3 | ERM Water Mist System | ERM Water Mist System |  | NS | [7 empty] | 2020-07-07
4.4 | Date Last Tested: | Date Last Tested: |  | NS | [7 empty] | 2020-07-07
4.5 | Other | Other |  | NS | [7 empty] | 2020-07-07
2020-07-07
C5 Safety Equipment Locker / Fire Station | [11 empty] | 2020-07-07
5.1 | Fire Station / Locker Condition | Fire Station / Locker Condition | Clean, tidy. | 2 | [7 empty] | 2020-07-07
5.2 | Fire Suits | Fire Suits | Generally acceptable condition. Single suit to be replaced. | 3 |  | n | [5 empty] | 2020-07-07
5.3 | Nr onboard: | Nr onboard: | [9 empty] | 2020-07-07
5.4 | BA Sets | BA Sets |  | 1 | [7 empty] | 2020-07-07
5.5 | No. onbd / Spare cyls / Last Serviced | No. onbd / Spare cyls / Last Serviced | [9 empty] | 2020-07-07
5.6 | BA Cylinders | BA Cylinders | All within pressure and annual test. | 1 | [7 empty] | 2020-07-07
5.7 | BA Cylinder pressure tests in date | BA Cylinder pressure tests in date | As above | 1 | [7 empty] | 2020-07-07
5.8 | EEBDS | EEBDS | [9 empty] | 2020-07-07
5.9 | No. units onbd / Last Serviced: | No. units onbd / Last Serviced: | [9 empty] | 2020-07-07
5.1 | Chemical Suits | Chemical Suits | [9 empty] | 2020-07-07
5.11 | No. units onbd / Last Serviced: | No. units onbd / Last Serviced: | [9 empty] | 2020-07-07
5.12 | Fire Alarm Panel | Fire Alarm Panel | [9 empty] | 2020-07-07
5.13 | Other | Other | [9 empty] | 2020-07-07
2020-07-07
C6 Portable Extingsuihsers / Hoses / Hydrants / Foam Applicators | [11 empty] | 2020-07-07
6.1 | Dry Powder | Dry Powder |  | 1 | [7 empty] | 2020-07-07
6.2 | Last service: | Last service: |  | 1 | [7 empty] | 2020-07-07
6.3 | Hydrants | Hydrants |  | 2 | [7 empty] | 2020-07-07
6.4 | Hoses / Boxes | Hoses / Boxes |  | 1 | [7 empty] | 2020-07-07
6.5 | Foam Applicators | Foam Applicators |  | 1 | [7 empty] | 2020-07-07
6.6 | Other | Other | All found in generally good condition. To be monitored continuously. | 1 | [7 empty] | 2020-07-07
2020-07-07
C7 Emergency Equipment | [11 empty] | 2020-07-07
7.1 | Emergency Generator | Generator | Tested during inspection. | 1 | [7 empty] | 2020-07-07
7.2 | Date last load tested: | Date last load tested: | 19.12.2015 | 1 | [7 empty] | 2020-07-07
7.3 | Air Compressor | Air Compressor | Used during inspection (see not on flooded store room) | 1 | [7 empty] | 2020-07-07
7.4 | Date last load tested: | Date last load tested: |  | NS | [7 empty] | 2020-07-07
7.5 | Fire Pump | Fire Pump |  | 1 | [7 empty] | 2020-07-07
7.6 | Date last load tested: | Date last load tested: |  | NS | [7 empty] | 2020-07-07
7.7 | Emergency Lighting | Emergency Lighting |  | NS | [7 empty] | 2020-07-07
7.8 | Emergency Alarms / Bells | Emergency Alarms / Bells |  | NS | [7 empty] | 2020-07-07
7.9 | Fire Dampers Accommodation | Fire Dampers Accommodation | Acceptable condition only. Repair plan to be implemented. | 2 | [7 empty] | 2020-07-07
7.1 | Quick Closing System | Quick Closing System |  | NS | [7 empty] | 2020-07-07
7.11 | Verification Test | Verification Test by TSI |  | NS | [7 empty] | 2020-07-07
7.12 | Emergency Batteries | Emergency Batteries |  | 1 | [7 empty] | 2020-07-07
7.13 | Deck Safety Line | Deck Safety Line |  | NS | [7 empty] | 2020-07-07
7.14 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
C8 Other Safety Equipment | [11 empty] | 2020-07-07
8.1 | Gas Analyzer | Gas Analyzer |  | 1 | [7 empty] | 2020-07-07
8.2 | Date last calibrated: | Date last calibrated: | 2015-11-01 | 1 | [7 empty] | 2020-07-07
8.3 | O2 Meter | O2 Meter | (Draeger Multimeter Unit) | 1 | [7 empty] | 2020-07-07
8.4 | Date last calibrated: | Date last calibrated: | 2015-11-01 | 1 | [7 empty] | 2020-07-07
8.5 | Press / Temp Calibrator | Press / Temp Calibrator |  | NS | [7 empty] | 2020-07-07
8.6 | Date last calibrated: | Date last calibrated: |  | NS | [7 empty] | 2020-07-07
8.7 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07

## D. Machinery Spaces & Equipment
D. MACHINERY SPACES & EQUIIPMENT
THIS SECTION IS NOT PRINTED
D1 General - Ventilation / Lighting / Cosmetic / Bilge Wells / Savealls / Identification | D1 General - Ventilation / Lighting / Cosmetic / Bilge Wells / Savealls / Identification | D1 General - Ventilation / Lighting / Cosmetic / Bilge Wells / Savealls / Identification
ID | Item |  | Observations & Corrective Action Required |  |  |  | 19.13.3015 |  |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) | Rating | ID | Observations & Corrective Action Required | Closeout Date | 2020-07-07
1.1 | Cleanliness | Cleanliness | Workshops and machinery spaces in generally unacceptable state of cleanliness. Multiple half-empty containers of oil found in various locations, waste equipment and rags "tucked" between frames. During inspection, ships personnel flooded the electricians store resulting in large amounts of water around entire macinery space. 90% of deck plates unscrewed, although it is noted that repair works on these were underway. Engine room and attached spaces to be thoroughly cleaned, all waste removed and a regular cleaning routine to be established. All deck pleates and grill to be screwed down. |  |  |  | 4 |  |  | y | 30 | 4 | 1.1 | Workshops and machinery spaces in generally unacceptable state of cleanliness. Multiple half-empty containers of oil found in various locations, waste equipment and rags "tucked" between frames. During inspection, ships personnel flooded the electricians store resulting in large amounts of water around entire macinery space. 90% of deck plates unscrewed, although it is noted that repair works on these were underway. Engine room and attached spaces to be thoroughly cleaned, all waste removed and a regular cleaning routine to be established. All deck pleates and grill to be screwed down. | 2020-08-06 | 2020-07-07
1.2 | Cosmetic / Coatings | Cosmetic / Coatings | Day-tank coating to be renewed. |  |  |  | 3 |  |  | n | [5 empty] | 2020-07-07
1.3 | Lighting | Lighting |  |  |  |  | 1 | [8 empty] | 2020-07-07
1.4 | Bilges / Tank Tops / Savealls | Bilges / Tank Tops / Savealls |  |  |  |  | 1 | [8 empty] | 2020-07-07
1.5 | Pipeline / Valve Identification | Pipeline / Valve Identification | Lagging missing from various apparently "disused" steam piping. Piping either to be physically blanked off to prevent unintended use, or lagging is to be replaced. |  |  |  | 3 |  |  | y | 60 | 3 | 1.5 | Lagging missing from various apparently "disused" steam piping. Piping either to be physically blanked off to prevent unintended use, or lagging is to be replaced. | 2020-09-05 | 2020-07-07
1.6 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D2 Fuel Systems | [15 empty] | 2020-07-07
2.1 | Transfer / Pumping Systems | Transfer / Pumping Systems | Prior to inspection oil spill during bunkering operation. Investigation ongoing |  |  |  | 3 | [8 empty] | 2020-07-07
2.2 | Purification / Treatment Plants | Purification / Treatment Plants | Dirty oil containers to be removed from Purifier Room |  |  |  | 2 | [8 empty] | 2020-07-07
2.3 | Piping / Valves / Controllers | Piping / Valves / Controllers |  |  |  |  | 1 | [8 empty] | 2020-07-07
2.4 | Heaters / Viscometers | Heaters / Viscometers |  |  |  |  | NS | [8 empty] | 2020-07-07
2.5 | Filtration Plants | Filtration Plants |  |  |  |  | NS | [8 empty] | 2020-07-07
2.6 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D3 Lube Oil Systems | [15 empty] | 2020-07-07
3.1 | Transfer / Pumping Systems | Transfer / Pumping Systems |  |  |  |  | 1 | [8 empty] | 2020-07-07
3.2 | Purification Plants | Purification Plants |  |  |  |  | NS | [8 empty] | 2020-07-07
3.3 | Piping / Valves / Controllers | Piping / Valves / Controllers |  |  |  |  | 1 | [8 empty] | 2020-07-07
3.4 | Heaters / Coolers | Heaters / Coolers |  |  |  |  | NS | [8 empty] | 2020-07-07
3.5 | Filtration Plants | Filtration Plants |  |  |  |  | NS | [8 empty] | 2020-07-07
3.6 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D4 Sea Water systems | [15 empty] | 2020-07-07
4.1 | Pumps | Pumps | No reported issues |  |  |  | 1 | [8 empty] | 2020-07-07
4.2 | Shipside Connects / Sea Chests | Shipside Connects / Sea Chests |  |  |  |  | 1 | [8 empty] | 2020-07-07
4.3 | Piping / Valves / Controllers | Piping / Valves / Controllers |  |  |  |  | 1 | [8 empty] | 2020-07-07
4.4 | Coolers | Coolers |  |  |  |  | 1 | [8 empty] | 2020-07-07
4.5 | Filters | [5 empty] | 1 | [8 empty] | 2020-07-07
4.6 | ICCP / MGPS | [5 empty] | 1 | [8 empty] | 2020-07-07
4.7 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D5 Fresh Water Cooling Systems | [15 empty] | 2020-07-07
5.1 | Pumps | Pumps |  |  |  |  | 1 | [8 empty] | 2020-07-07
5.2 | Piping / Valves / Controllers | Piping / Valves / Controllers |  |  |  |  | 1 | [8 empty] | 2020-07-07
5.3 | Coolers / Heaters | Coolers / Heaters |  |  |  |  | 1 | [8 empty] | 2020-07-07
5.4 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D6 Bilge / Ballast / Sludge / Waste Disposal Systems | D6 Bilge / Ballast / Sludge / Waste Disposal Systems | D6 Bilge / Ballast / Sludge / Waste Disposal Systems | D6 Bilge / Ballast / Sludge / Waste Disposal Systems | D6 Bilge / Ballast / Sludge / Waste Disposal Systems | D6 Bilge / Ballast / Sludge / Waste Disposal Systems | D6 Bilge / Ballast / Sludge / Waste Disposal Systems | D6 Bilge / Ballast / Sludge / Waste Disposal Systems | D6 Bilge / Ballast / Sludge / Waste Disposal Systems | [7 empty] | 2020-07-07
6.1 | Bilge/GS/Fire Pumps | Bilge/GS/Fire Pumps |  |  |  |  | 1 | [8 empty] | 2020-07-07
6.2 | Sludge Pumps | Sludge Pumps |  |  |  |  | 1 | [8 empty] | 2020-07-07
6.3 | Ballast Pumps | Ballast Pumps |  |  |  |  | 1 | [8 empty] | 2020-07-07
6.4 | Incinerator Plant | Incinerator Plant |  |  |  |  | 1 | [8 empty] | 2020-07-07
6.5 | Oil Water Separator | Oil Water Separator | Test brush to be replaced |  |  |  | 3 |  |  | y | 30 | 3 | 6.5 | Test brush to be replaced | 2020-08-06 | 2020-07-07
6.6 | Date OWS last opened / inspected: | Date OWS last opened / inspected: |  |  |  |  | 1 | [8 empty] | 2020-07-07
6.7 | Sewage Plant | Sewage Plant |  |  |  |  | 1 | [8 empty] | 2020-07-07
6.8 | Piping / Valves / Controllers | Piping / Valves / Controllers |  |  |  |  | 1 | [8 empty] | 2020-07-07
6.9 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D7 Domestic Water Systems | [15 empty] | 2020-07-07
7.1 | FWG | FWG |  |  |  |  | NS | [8 empty] | 2020-07-07
7.2 | Calorifier | Calorifier |  |  |  |  | NS | [8 empty] | 2020-07-07
7.3 | Hydrophores | Hydrophores |  |  |  |  | NS | [8 empty] | 2020-07-07
7.4 | Sterilizer / Filters | Sterilizer / Filters |  |  |  |  | NS | [8 empty] | 2020-07-07
7.5 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D8 Compressed Air Systems | [15 empty] | 2020-07-07
8.1 | Main / Aux Start Air Systems | Main / Aux Start Air Systems |  |  |  |  | NS | [8 empty] | 2020-07-07
8.2 | Control Air Systems | Control Air Systems |  |  |  |  | NS | [8 empty] | 2020-07-07
8.3 | Control Air Piping / Filters | Control Air Piping / Filters |  |  |  |  | NS | [8 empty] | 2020-07-07
8.4 | Gen Deck Air / Service Systems | Gen Deck Air / Service Systems |  |  |  |  | NS | [8 empty] | 2020-07-07
8.5 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D9 Steam & Condensate Systems | [15 empty] | 2020-07-07
9.1 | OF Boiler / Fittings | OF Boiler / Fittings | Ongoing boiler issues. To be included in next inspection report. |  |  |  | 3 | [8 empty] | 2020-07-07
9.2 | EGE / Fittings | EGE / Fittings |  |  |  |  | NS | [8 empty] | 2020-07-07
9.3 | Hotwell / Cascade Tnk | Hotwell / Cascade Tnk |  |  |  |  | NS | [8 empty] | 2020-07-07
9.4 | Valves / Piping | Valves / Piping |  |  |  |  | NS | [8 empty] | 2020-07-07
9.5 | Condensers / Heaters / Coils | Condensers / Heaters / Coils |  |  |  |  | NS | [8 empty] | 2020-07-07
9.6 | Pumps | Pumps |  |  |  |  | NS | [8 empty] | 2020-07-07
9.7 | Boiler Water Analysis | Boiler Water Analysis |  |  |  |  | NS | [8 empty] | 2020-07-07
9.8 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D10 Exhaust Systems | [15 empty] | 2020-07-07
10.1 | ME Piping / Brackets / Insulation | ME Piping / Brackets / Insulation |  |  |  |  | 1 | [8 empty] | 2020-07-07
10.2 | Aux Piping / Brackets / Insulation | Aux Piping / Brackets / Insulation |  |  |  |  | 1 | [8 empty] | 2020-07-07
10.3 | Rain Traps / Water Drains | Rain Traps / Water Drains |  |  |  |  | 1 | [8 empty] | 2020-07-07
10.4 | Soot tank / piping / valves | Soot tank / piping / valves |  |  |  |  | 1 | [8 empty] | 2020-07-07
10.5 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D11 Steering Systems | [15 empty] | 2020-07-07
11.1 | Telemotor (Rudder Position Feed Back Unit) | Telemotor (Rudder Position Feed Back Unit) |  |  |  |  | 1 | [8 empty] | 2020-07-07
11.2 | Steering Gear | Steering Gear |  |  |  |  | 1 | [8 empty] | 2020-07-07
11.3 | Emergency Operation | Emergency Operation |  |  |  |  | 1 | [8 empty] | 2020-07-07
11.4 | Communication | Communication |  |  |  |  | 1 | [8 empty] | 2020-07-07
11.5 | Oil Analysis | Oil Analysis |  |  |  |  | NS | [8 empty] | 2020-07-07
11.6 | Date last sampled: | Date last sampled: |  |  |  |  | NS | [8 empty] | 2020-07-07
11.7 | Other | Other | Steering flat and equipment found to be in very well maintained condition |  |  |  | 1 | [8 empty] | 2020-07-07
2020-07-07
D12 Bowthruster(s) | [15 empty] | 2020-07-07
12.1 | Electrical Equipment | Electrical Equipment |  |  |  |  | 1 | [8 empty] | 2020-07-07
12.2 | Hydraulic Equipment | Hydraulic Equipment |  |  |  |  | 1 | [8 empty] | 2020-07-07
12.3 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D13 Store Rooms: Spares, Stock Control and Stowage Procedures | [15 empty] | 2020-07-07
13.1 | Safe Stowage | Safe Stowage | Evidence that items are not being stowed for sea. Crew to be reminded of the importance of correct stowage of stores. |  |  |  | 3 |  |  | y | 30 | 3 | 13.1 | Evidence that items are not being stowed for sea. Crew to be reminded of the importance of correct stowage of stores. | 2020-08-06 | 2020-07-07
13.2 | Tidiness / Condition of spares | Tidiness / Condition of spares |  |  |  |  | 2 | [8 empty] | 2020-07-07
13.3 | Chemical Storage / Safety | Chemical Storage / Safety |  |  |  |  | 1 | [8 empty] | 2020-07-07
13.4 | Freon Gas Storage / Safety | Freon Gas Storage / Safety |  |  |  |  | NS | [8 empty] | 2020-07-07
13.5 | Welding Gas Storage / Safety | Welding Gas Storage / Safety | Open container of oil stowed in same space as welding gas. To be removed immediately. |  |  |  | 4 |  |  | y | 5 | 4 | 13.5 | Open container of oil stowed in same space as welding gas. To be removed immediately. | 2020-07-12 | 2020-07-07
13.6 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D14 Workshop(s),Engine Room Cranes, Special Equipment | [15 empty] | 2020-07-07
14.1 | Safe Stowage | Safe Stowage |  |  |  |  | 2 | [8 empty] | 2020-07-07
14.2 | Tidiness | Tidiness |  |  |  |  | 3 | [8 empty] | 2020-07-07
14.3 | Condition Hand Tools | Condition Hand Tools |  |  |  |  | 1 | [8 empty] | 2020-07-07
14.4 | Condition Mechanical Tools | Condition Mechanical Tools |  |  |  |  | 2 | [8 empty] | 2020-07-07
14.5 | Welding Equipment | Welding Equipment |  |  |  |  | NS | [8 empty] | 2020-07-07
14.6 | Injector Test Equipment | Injector Test Equipment |  |  |  |  | NS | [8 empty] | 2020-07-07
14.7 | Engine Room Crane(s) | Engine Room Crane(s) |  |  |  |  | 1 | [8 empty] | 2020-07-07
14.8 | Date Last Load Test | Date Last Load Test |  |  |  |  | NS | [8 empty] | 2020-07-07
14.9 | Condition Check of Limit Switch | Condition Check of Limit Switch |  |  |  |  | NS | [8 empty] | 2020-07-07
14.1 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D15 Engine Control Room | [15 empty] | 2020-07-07
15.1 | Lighting | Lighting |  |  |  |  | 1 | [8 empty] | 2020-07-07
15.2 | Tidiness | Tidiness |  |  |  |  | 2 | [8 empty] | 2020-07-07
15.3 | Consuls / Swbds | Consuls / Swbds |  |  |  |  | 1 | [8 empty] | 2020-07-07
15.4 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D16 Main Engine | [15 empty] | 2020-07-07
16.1 | Cosmetic Condition | Cosmetic Condition |  |  |  |  | 1 | [8 empty] | 2020-07-07
16.2 | Performance | Performance |  |  |  |  | NS | [8 empty] | 2020-07-07
16.3 | Turbocharging Equipment | Turbocharging Equipment |  |  |  |  | NS | [8 empty] | 2020-07-07
16.4 | Lubricator | Lubricator |  |  |  |  | NS | [8 empty] | 2020-07-07
16.5 | Fuel Equipment | Fuel Equipment |  |  |  |  | 2 | [8 empty] | 2020-07-07
16.6 | System Oil Analysis | System Oil Analysis |  |  |  |  | NS | [8 empty] | 2020-07-07
16.7 | Date last sampled: | Date last sampled: |  |  |  |  | NS | [8 empty] | 2020-07-07
16.8 | Cooling Water Analysis | Cooling Water Analysis |  |  |  |  | NS | [8 empty] | 2020-07-07
16.9 | Maintenance | Maintenance |  |  |  |  | 2 | [8 empty] | 2020-07-07
16.1 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D17 Shafting / Propellor / Stern Stube | [15 empty] | 2020-07-07
17.1 | Pedestal Bearings | Pedestal Bearings |  |  |  |  | NS | [8 empty] | 2020-07-07
17.2 | Stern Tube Seal | Stern Tube Seal |  |  |  |  | NS | [8 empty] | 2020-07-07
17.3 | Oil Analysis | Oil Analysis |  |  |  |  | NS | [8 empty] | 2020-07-07
17.4 | Date last sampled: | Date last sampled: |  |  |  |  | NS | [8 empty] | 2020-07-07
17.5 | Propeller | Propeller |  |  |  |  | NS | [8 empty] | 2020-07-07
17.6 | Shaft Earthing | Shaft Earthing |  |  |  |  | NS | [8 empty] | 2020-07-07
17.7 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D18 Auxiliary Machinery | [15 empty] | 2020-07-07
18.1 | Ancillary Supplies | Ancillary Supplies |  |  |  |  | 2 | [8 empty] | 2020-07-07
18.2 | Cooling Water Analysis | Cooling Water Analysis |  |  |  |  | NS | [8 empty] | 2020-07-07
18.3 | AE Flat Cosmetic Condition | AE Flat Cosmetic Condition |  |  |  |  | 2 | [8 empty] | 2020-07-07
18.4 | AE1 Condition / Performance | AE1 Condition / Performance |  |  |  |  | NS | [8 empty] | 2020-07-07
18.5 | AE1 Maintenance | AE1 Maintenance |  |  |  |  | 2 | [8 empty] | 2020-07-07
18.6 | AE1 Oil Analysis | AE1 Oil Analysis |  |  |  |  | NS | [8 empty] | 2020-07-07
18.7 | Date last sampled: | Date last sampled: |  |  |  |  | NS | [8 empty] | 2020-07-07
18.8 | AE2 Condition / Performance | AE2 Condition / Performance |  |  |  |  | NS | [8 empty] | 2020-07-07
18.9 | AE2 Maintenance | AE2 Maintenance |  |  |  |  | NS | [8 empty] | 2020-07-07
18.1 | AE2 Oil Analysis | AE2 Oil Analysis |  |  |  |  | NS | [8 empty] | 2020-07-07
18.11 | Date last sampled: | Date last sampled: |  |  |  |  | NS | [8 empty] | 2020-07-07
18.12 | SHAFT GENERATOR | SHAFT GENERATOR |  |  |  |  | NS | [8 empty] | 2020-07-07
18.13 | Condition / Performance | Condition / Performance |  |  |  |  | NS | [8 empty] | 2020-07-07
18.14 | Oil Analysis | Oil Analysis |  |  |  |  | NS | [8 empty] | 2020-07-07
18.15 | Date last sampled: | Date last sampled: |  |  |  |  | NS | [8 empty] | 2020-07-07
18.16 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
D19 Automation / Alarm Systems | [15 empty] | 2020-07-07
19.1 | ME Control | ME Control |  |  |  |  | NS | [8 empty] | 2020-07-07
19.2 | Auxiliary Control | Auxiliary Control |  |  |  |  | NS | [8 empty] | 2020-07-07
19.3 | Alarm Systems | Alarm Systems |  |  |  |  | NS | [8 empty] | 2020-07-07
19.4 | Bilge / Ballast Systems | Bilge / Ballast Systems |  |  |  |  | NS | [8 empty] | 2020-07-07
19.5 | Other | Other | Ongoing issues with Norcontrol automation and UMS systems, investigations and repairs underway during inspection, Condition in place to end Feb 2016. |  |  |  | 4 |  |  | y |  | 4 | 19.5 | Ongoing issues with Norcontrol automation and UMS systems, investigations and repairs underway during inspection, Condition in place to end Feb 2016. | 2020-07-07 | 2020-07-07
2020-07-07
D20 Electrical | [15 empty] | 2020-07-07
20.1 | Main Switchboard | Main Switchboard |  |  |  |  | NS | [8 empty] | 2020-07-07
20.2 | Aux Switchboards / Starters | Aux Switchboards / Starters |  |  |  |  | NS | [8 empty] | 2020-07-07
20.3 | Alternators | Alternators |  |  |  |  | NS | [8 empty] | 2020-07-07
20.4 | Electric Motors | Electric Motors |  |  |  |  | NS | [8 empty] | 2020-07-07
20.5 | Insulation / Cabling | Insulation / Cabling |  |  |  |  | NS | [8 empty] | 2020-07-07
20.6 | Transformers | Transformers |  |  |  |  | NS | [8 empty] | 2020-07-07
20.7 | Other | Other |  |  |  |  | NA | [8 empty] | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07

## E. Accommodation
E. ACCOMMODATION
THIS SECTION IS NOT PRINTED
E1 Accommodation Internal Areas | D1 General - Ventilation / Lighting / Cosmetic / Bilge Wells / Savealls / Identification | D1 General - Ventilation / Lighting / Cosmetic / Bilge Wells / Savealls / Identification
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) | Rating | ID | Observations & Corrective Action Required | Closeout Date | 2020-07-07
1.1 | Mess Rooms / Lounges | Mess Rooms / Lounges |  | 1 | [7 empty] | 2020-07-07
1.2 | Recreation / Gym Room | Recreation / Gym Room | Poor condition, with rubbish being stored in space. Tidy. | 3 | [7 empty] | 2020-07-07
1.3 | Alleyways / Stairways / Decks | Alleyways / Stairways / Decks |  | 1 | [7 empty] | 2020-07-07
1.4 | Duct Spaces | Duct Spaces |  | NS | [7 empty] | 2020-07-07
1.5 | Cabins - General Condition | Cabins |  | NS | [7 empty] | 2020-07-07
1.6 | Ablutions − Common | Ablutions − Private / Common |  | 2 | [7 empty] | 2020-07-07
1.7 | Change Rooms | Change Rooms |  | 2 | [7 empty] | 2020-07-07
1.8 | Hospital / Dispensary | Hospital / Dispensary | Accessway to hospital obstructed by piles of timber. To be removed immediately and stowed in a more appropriate space. | 4 |  | y | 10 | 4 | 1.8 | Accessway to hospital obstructed by piles of timber. To be removed immediately and stowed in a more appropriate space. | 2020-07-17 | 2020-07-07
1.9 | Medical Cert Expiry date: | Medical Cert Expiry date: |  | 1 | [7 empty] | 2020-07-07
1.1 | Ships Office | Ships Office |  | 2 | [7 empty] | 2020-07-07
1.11 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
E2 Hotel Services | [11 empty] | 2020-07-07
2.1 | Laundry and Equipment | Laundry and Equipment |  | 1 | [7 empty] | 2020-07-07
2.2 | AC Room/ Equipment | AC Room/ Equipment |  | 1 | [7 empty] | 2020-07-07
2.3 | Prov Fridge/ Dry Store Spaces | Prov Fridge/ Dry Store Spaces | Found in exceptionally good condition. | 1 | [7 empty] | 2020-07-07
2.4 | Temperatures: | Temperatures: |  | 1 | [7 empty] | 2020-07-07
2.5 | Galley / Pantry Area | Galley / Pantry Area | Very good condition of cleanliness | 1 | [7 empty] | 2020-07-07
2.6 | Galley Equipment | Galley Equipment | No issues reported by Cook | 1 | [7 empty] | 2020-07-07
2.7 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
E3 Living and Working Environment | [11 empty] | 2020-07-07
3.1 | Comfort / Ergonomics | Comfort / Ergonomics |  | 2 | [7 empty] | 2020-07-07
3.2 | Catering Hygiene | Catering Hygiene |  | 1 | [7 empty] | 2020-07-07
3.3 | Living Areas Hygiene | Living Areas Hygiene |  | 1 | [7 empty] | 2020-07-07
3.4 | Furniture / Furnishings | Furniture / Furnishings | Newly built furnishings being maintained well. | 1 | [7 empty] | 2020-07-07
3.5 | Ventilation / Lighting | Ventilation / Lighting |  | 1 | [7 empty] | 2020-07-07
3.6 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
E4 Cabins: Cleanliness & Hygiene, General Condition | [11 empty] | 2020-07-07
4.1 |  |  | To be inspected at a later date. | [8 empty] | 2020-07-07
4.2 | [11 empty] | 2020-07-07
4.3 | [11 empty] | 2020-07-07
4.4 | [11 empty] | 2020-07-07
4.5 | [11 empty] | 2020-07-07
4.6 | [11 empty] | 2020-07-07
4.7 | [11 empty] | 2020-07-07
4.8 | [11 empty] | 2020-07-07
4.9 | [11 empty] | 2020-07-07
4.1 | [11 empty] | 2020-07-07
4.11 | [11 empty] | 2020-07-07
4.12 | [11 empty] | 2020-07-07
4.13 | [11 empty] | 2020-07-07
4.14 | [11 empty] | 2020-07-07
4.15 | [11 empty] | 2020-07-07
4.16 | [11 empty] | 2020-07-07
4.17 | [11 empty] | 2020-07-07
4.18 | [11 empty] | 2020-07-07
4.19 | [11 empty] | 2020-07-07
4.2 | [11 empty] | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07

## F. Certification
E. ACCOMMODATION
THIS SECTION IS NOT PRINTED
E1 Accommodation Internal Areas | D1 General - Ventilation / Lighting / Cosmetic / Bilge Wells / Savealls / Identification | D1 General - Ventilation / Lighting / Cosmetic / Bilge Wells / Savealls / Identification
ID | Item |  | Observations & Corrective Action Required | 19.13.3015 |  | Raise Section H Defect? (Y / N) | Target Closeout Timeframe (days) | Rating | ID | Observations & Corrective Action Required | Closeout Date | 2020-07-07
1.1 | Mess Rooms / Lounges | Mess Rooms / Lounges |  | 1 | [7 empty] | 2020-07-07
1.2 | Recreation / Gym Room | Recreation / Gym Room | Poor condition, with rubbish being stored in space. Tidy. | 3 | [7 empty] | 2020-07-07
1.3 | Alleyways / Stairways / Decks | Alleyways / Stairways / Decks |  | 1 | [7 empty] | 2020-07-07
1.4 | Duct Spaces | Duct Spaces |  | NS | [7 empty] | 2020-07-07
1.5 | Cabins - General Condition | Cabins |  | NS | [7 empty] | 2020-07-07
1.6 | Ablutions − Common | Ablutions − Private / Common |  | 2 | [7 empty] | 2020-07-07
1.7 | Change Rooms | Change Rooms |  | 2 | [7 empty] | 2020-07-07
1.8 | Hospital / Dispensary | Hospital / Dispensary | Accessway to hospital obstructed by piles of timber. To be removed immediately and stowed in a more appropriate space. | 4 |  | y | 10 | 4 | 1.8 | Accessway to hospital obstructed by piles of timber. To be removed immediately and stowed in a more appropriate space. | 2020-07-17 | 2020-07-07
1.9 | Medical Cert Expiry date: | Medical Cert Expiry date: |  | 1 | [7 empty] | 2020-07-07
1.1 | Ships Office | Ships Office |  | 2 | [7 empty] | 2020-07-07
1.11 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
E2 Hotel Services | [11 empty] | 2020-07-07
2.1 | Laundry and Equipment | Laundry and Equipment |  | 1 | [7 empty] | 2020-07-07
2.2 | AC Room/ Equipment | AC Room/ Equipment |  | 1 | [7 empty] | 2020-07-07
2.3 | Prov Fridge/ Dry Store Spaces | Prov Fridge/ Dry Store Spaces | Found in exceptionally good condition. | 1 | [7 empty] | 2020-07-07
2.4 | Temperatures: | Temperatures: |  | 1 | [7 empty] | 2020-07-07
2.5 | Galley / Pantry Area | Galley / Pantry Area | Very good condition of cleanliness | 1 | [7 empty] | 2020-07-07
2.6 | Galley Equipment | Galley Equipment | No issues reported by Cook | 1 | [7 empty] | 2020-07-07
2.7 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
E3 Living and Working Environment | [11 empty] | 2020-07-07
3.1 | Comfort / Ergonomics | Comfort / Ergonomics |  | 2 | [7 empty] | 2020-07-07
3.2 | Catering Hygiene | Catering Hygiene |  | 1 | [7 empty] | 2020-07-07
3.3 | Living Areas Hygiene | Living Areas Hygiene |  | 1 | [7 empty] | 2020-07-07
3.4 | Furniture / Furnishings | Furniture / Furnishings | Newly built furnishings being maintained well. | 1 | [7 empty] | 2020-07-07
3.5 | Ventilation / Lighting | Ventilation / Lighting |  | 1 | [7 empty] | 2020-07-07
3.6 | Other | Other |  | NA | [7 empty] | 2020-07-07
2020-07-07
E4 Cabins: Cleanliness & Hygiene, General Condition | [11 empty] | 2020-07-07
4.1 |  |  | To be inspected at a later date. | [8 empty] | 2020-07-07
4.2 | [11 empty] | 2020-07-07
4.3 | [11 empty] | 2020-07-07
4.4 | [11 empty] | 2020-07-07
4.5 | [11 empty] | 2020-07-07
4.6 | [11 empty] | 2020-07-07
4.7 | [11 empty] | 2020-07-07
4.8 | [11 empty] | 2020-07-07
4.9 | [11 empty] | 2020-07-07
4.1 | [11 empty] | 2020-07-07
4.11 | [11 empty] | 2020-07-07
4.12 | [11 empty] | 2020-07-07
4.13 | [11 empty] | 2020-07-07
4.14 | [11 empty] | 2020-07-07
4.15 | [11 empty] | 2020-07-07
4.16 | [11 empty] | 2020-07-07
4.17 | [11 empty] | 2020-07-07
4.18 | [11 empty] | 2020-07-07
4.19 | [11 empty] | 2020-07-07
4.2 | [11 empty] | 2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07
2020-07-07

## G. Photo Report
G. PHOTO REPORT
ID | Area | ERM / HOLD CO2 | Observation, Corrective Action
PHOTO
ID | Area | ERM / HOLD CO2 | Observation, Corrective Action
PHOTO
ID | Area | ERM / HOLD CO2 | Observation, Corrective Action
PHOTO

## H. Defect Report
H. DEFECT REPORT
| Ship | TIARE MOANA
| Inspection Date(s) | 2015-12-19
| Port | Auckland, New Zealand
During the above inspection, the following defects and/or issues were noted. All defects should be rectified at the earliest practical opportunity and corrective action taken noted on this form. If, for any reason, the defect cannot be rectified out by the target closeout-date below the Master/Chief Engineer is to inform the Technical Department.
The defects raised in this report are to be included in the ships live defect report, which is to be forwarded to the Technical Department weekly.
H1 All "Major Issues" / "4"
ID | Issue/ Observation & Corrective Action Required | Target Closeout Date | Corrective Action Taken | Actual Closeout Date | Master / Chief Engineer
A
4.7 | Mooring winch operator platforms: Wooden board that makes up middle platform is missing, causing the rest to move away from their seating. Middle board to be replaced immediately, and the condition of all remaining boards to be inspected and repairs or adjustments made to ensure they cannot "slide" free. | 2016-01-18
15.1 | On our arrival there was no gangway watchman present, he had been removed to carry out other tasks by the Chief Officer. The Visitor Record is not being consistently completed. All crew are to be reminded of the requirements of ISPS with respect to Access Control and Safety. Gangway watch crew are to be reminded to NEVER leave the access point. | 2016-01-23
16.1.6 | At completion of cargo operations, CH1 hatch cover was severely damaged, resulting in delay of approx 2 days. | 2016-01-13 | Repairs carried out prior to departure | 2015-12-22 | Super.
16.1.12 | Many hatch cover cleats either missing or damaged. Understood repair plan in place, to be monitored closely. | 2016-05-12
19.7 | Significant corrosion around deck structures, including fire flaps, doors ladders and lifting lugs. Chief Officer to carry out a full inspection of the deck area and to prepare and submit a repair plan to the Technical Department. | 2016-02-12
20.4 | General housekeeping to be improved. Paint to be properly stowed, and crew to be reminded of the importance of doing so. | 2016-02-12
20.9 | Half-full drum of waste oil and dirty rags being stored in this space. To be removed immediately and crew to be reminded that this is not acceptable at any time. | 2016-01-23
20.12 | Almost all of the ships vertical escapes have no safety chain at their upper end. To be ordered and installed. Escape from ER Lower Deck Fwd Stbd, plating corroded through. To be investigated. | 2016-02-12
25.4 | Masters night orders only completed sporadically. To be completed every night the vessel is at sea. | 2016-01-14
D
1.1 | Workshops and machinery spaces in generally unacceptable state of cleanliness. Multiple half-empty containers of oil found in various locations, waste equipment and rags "tucked" between frames. During inspection, ships personnel flooded the electricians store resulting in large amounts of water around entire macinery space. 90% of deck plates unscrewed, although it is noted that repair works on these were underway. Engine room and attached spaces to be thoroughly cleaned, all waste removed and a regular cleaning routine to be established. All deck pleates and grill to be screwed down. | 2016-02-12
13.5 | Open container of oil stowed in same space as welding gas. To be removed immediately. | 2016-01-18
19.5 | Ongoing issues with Norcontrol automation and UMS systems, investigations and repairs underway during inspection, Condition in place to end Feb 2016. | 2016-01-13
H2 "Minor Issues" / "3" requiring specific corrective action
ID | Issue/ Observation & Corrective Action Required | Target Closeout Date | Corrective Action Taken | Actual Closeout Date | Master / Chief Engineer
A
2.4 | Various External ladders in need of repair. All to be inspected and those in poor condition to be repaired. | 2016-04-12
3.2 | Midships Stbd Side: Various cracks, likely result of cargo damage. Chief Officer to inspect and arrange necessary repairs | 2016-04-12
14.7 | Some fire flaps found to be corroded. Rectification plan to be drawn up and submitted to Technical Department. | 2016-03-13
14.11 | Some fire flaps found to be corroded. Rectification plan to be drawn up and submitted to Technical Department. | 2016-03-13
20.4 | General housekeeping to be improved. Paint to be properly stowed, and crew to be reminded of the importance of doing so. | 2016-02-12
D
1.5 | Lagging missing from various apparently "disused" steam piping. Piping either to be physically blanked off to prevent unintended use, or lagging is to be replaced. | 2016-03-13
6.5 | Test brush to be replaced | 2016-02-12
13.1 | Evidence that items are not being stowed for sea. Crew to be reminded of the importance of correct stowage of stores. | 2016-02-12
CLOSE OUT
The Master confirms that the defects identified above have been addressed and corrective action taken has been listed above in sufficient detail to enable verification at future inspections. Where a listed defect has not been rectified to date, an entry has been made in the ship’s live defect log and a plan of action has been discussed and agreed with the Technical Department.
Master: